## Slide 1
Azure VM to AKS Migration
3-Tier Application Containerization & Cloud-Native Modernization
Management Presentation
Apache2 (Web) | Open Liberty (App) | PostgreSQL (Database)
From Virtual Machines to Kubernetes -- Scalable, Resilient, Automated
1 / 16

## Slide 2
Agenda
1. Executive Summary
2. Current Architecture (Azure VMs)
3. Target Architecture (AKS + Managed Services)
4. Migration Phases Overview
5. Phase 1 - Infrastructure Setup
6. Phase 2 - Data Migration
7. Phase 3 - Containerization & Deployment
8. Kubernetes Configuration
9. Auto-Scaling & High Availability
10. Security & Network Policies
11. Resource Allocation
12. Key Benefits
13. Risk Mitigation & Rollback
14. Timeline & Next Steps
2 / 16

## Slide 3
Executive Summary
Why migrate to Azure Kubernetes Service?
We are migrating our 3-tier application from Azure Virtual Machines to Azure Kubernetes Service (AKS) to achieve greater scalability, reliability, and operational efficiency while reducing infrastructure costs.
Scalability
Auto-scaling from 2 to 10 pods (Web)
Auto-scaling from 2 to 8 pods (App)
Scale based on CPU & memory metrics
Handle traffic spikes automatically
Reliability
Zero-downtime rolling deployments
Self-healing with health probes
Pod anti-affinity across nodes
Automated rollback capability
Cost Efficiency
Pay only for resources consumed
Managed PostgreSQL (no DB admin overhead)
Shared AKS cluster infrastructure
Reduced operational overhead
3 / 16

## Slide 4
Current Architecture
3-Tier Application on Azure Virtual Machines
Client
End Users / Browsers
VM: Apache2 (Web Tier)
Reverse Proxy Static Content SSL Termination
VM: Open Liberty (App Tier)
Java Application Server Business Logic REST APIs
VM: PostgreSQL (Database Tier)
Relational Database Data Persistence Manual Backups
Current Challenges:
Manual scaling requires VM provisioning (minutes to hours)
No auto-healing -- manual intervention for failures
Patching and OS updates require planned downtime
Limited resource utilization visibility
High operational overhead for VM management
4 / 16

## Slide 5
Target Architecture
AKS + Azure Managed Services
Azure Kubernetes Service (AKS)
Client
NGINX Ingress
Load Balancing TLS Termination Rate Limiting
Apache2 Pods
Reverse Proxy ClusterIP Service HPA: 2-10 pods Health Probes
Open Liberty Pods
Java App Server ClusterIP Service HPA: 2-8 pods Health Probes
Azure Database
PostgreSQL Flexible Managed Service SSL Required
5 / 16

## Slide 6
Migration Phases Overview
Structured 4-phase approach for safe migration
1
Phase 1
Infrastructure Setup
Azure Resource Group Container Registry (ACR) AKS Cluster (3 nodes) Managed PostgreSQL
2
Phase 2
Data Migration
pg_dump from source VM Restore to Azure PostgreSQL Data validation Connectivity testing
3
Phase 3
Containerize & Deploy
Build Docker images Push to ACR Deploy K8s manifests Configure networking
4
Phase 4
Verify & Optimize
Health check validation Performance testing Monitoring setup DNS cutover
6 / 16

## Slide 7
Phase 1: Infrastructure Setup
Azure resource provisioning via automated scripts
01-setup-resource-group.sh
Resource Group
Creates rg-app-migration
Region: East US
Tags for project tracking
02-setup-acr.sh
Container Registry
Azure Container Registry (ACR)
Standard SKU for image storage
Integrated with AKS
03-setup-aks.sh
AKS Cluster
3 nodes (Standard_DS2_v2)
2 vCPU, 7 GiB RAM per node
Kubernetes v1.29
Azure CNI networking
Managed identity enabled
Monitoring add-on
04-setup-postgres.sh
Managed PostgreSQL
Flexible Server (v16)
Standard_D2ds_v4 SKU
128 GB storage
SSL connections required
Firewall rules for AKS
7 / 16

## Slide 8
Phase 2: Data Migration
PostgreSQL data migration from VM to Azure Managed Service
Migration Process (07-migrate-data.sh)
Step 1: Connect to source PostgreSQL VM via SSH
Step 2: Run pg_dump to export the database
Step 3: Transfer dump file to local machine
Step 4: Restore to Azure Database for PostgreSQL
Step 5: Verify data integrity with row counts
Step 6: Test application connectivity
Target Database Configuration
Server: pg-app-migration.postgres.database.azure.com
Database: appdb
Admin User: pgadmin
PostgreSQL Version: 16
Extensions: PG_TRGM, BTREE_GIST, UUID_OSSP
Security Measures
SSL/TLS required for all connections
Firewall restricted to AKS outbound IPs
Credentials stored in K8s Secrets
Azure Key Vault integration (recommended)
8 / 16

## Slide 9
Phase 3: Containerization & Deployment
Docker images for each application tier
Apache2 Web Tier (docker/apache2/Dockerfile)
Base Image: httpd:2.4-alpine
Purpose: Reverse proxy to Open Liberty backend
Modules: proxy, proxy_http, proxy_balancer, rewrite, headers
Health Check: HTTP GET /health every 30s
Port: 80 (HTTP)
Features:
- Custom virtual host configuration
- Request logging
- Optional static content serving
- Optional SSL termination
Open Liberty App Tier (docker/openliberty/Dockerfile)
Base Image: open-liberty:kernel-slim-java17-openj9
Purpose: Java application server with business logic
JDBC Driver: PostgreSQL 42.7.3
Health Check: HTTP GET /health every 30s
Ports: 9080 (HTTP), 9443 (HTTPS)
Optimizations:
- Shared Class Cache (SCC) for fast startup
- JVM tuned for containers
- Non-root user (UID 1001)
- Feature auto-installation from server.xml
9 / 16

## Slide 10
Kubernetes Configuration
Deployment manifests and service topology
Resource | Name | Type | Details
Namespace | app-migration | Namespace | Isolated environment for all resources
Apache Deployment | apache-deployment | Deployment | 2 replicas, rolling update
Liberty Deployment | openliberty-deployment | Deployment | 2 replicas, rolling update
Apache Service | apache-service | ClusterIP | Port 80 internal routing
Liberty Service | openliberty-service | ClusterIP | Port 9080 internal routing
Ingress | app-ingress | Ingress | NGINX, external HTTP/HTTPS access
Apache HPA | apache-hpa | HPA | 2-10 pods, CPU 70% / Mem 80%
Liberty HPA | openliberty-hpa | HPA | 2-8 pods, CPU 60% / Mem 75%
Network Policy | apache-network-policy | NetworkPolicy | Ingress-only traffic to Apache
Network Policy | openliberty-network-policy | NetworkPolicy | Apache-only traffic to Liberty
ConfigMap | apache-config | ConfigMap | Apache environment settings
ConfigMap | openliberty-config | ConfigMap | App + DB connection config
Secret | db-credentials | Secret | DB_USER, DB_PASSWORD
10 / 16

## Slide 11
Auto-Scaling & High Availability
Horizontal Pod Autoscaler (HPA) configuration
Web Tier - Apache2 HPA
Min Replicas: 2 (always running for HA)
Max Replicas: 10 (peak traffic capacity)
CPU Target: 70% average utilization
Memory Target: 80% average utilization
Scale Up: Add up to 2 pods every 60s
Scale Down: Remove 1 pod every 120s
Stabilization (Up): 60 seconds
Stabilization (Down): 300 seconds (5 min)
App Tier - Open Liberty HPA
Min Replicas: 2 (always running for HA)
Max Replicas: 8 (peak load capacity)
CPU Target: 60% average utilization
Memory Target: 75% average utilization
Scale Up: Add up to 2 pods every 120s
Scale Down: Remove 1 pod every 180s
Stabilization (Up): 120 seconds
Stabilization (Down): 300 seconds (5 min)
High Availability Features: Pod anti-affinity (spread across nodes) | Rolling updates (zero-downtime) | Liveness/Readiness/Startup probes | 30-60s graceful shutdown
11 / 16

## Slide 12
Security & Network Policies
Defense-in-depth approach to application security
Network Traffic Flow (Enforced by NetworkPolicy)
Ingress Controller can send traffic to Apache pods (port 80)
Apache pods can only reach Open Liberty pods (port 9080)
Open Liberty pods can only reach PostgreSQL (port 5432) and HTTPS (443)
DNS resolution allowed for all pods (port 53)
All other traffic is denied by default
Security Features
Container Security:
- Non-root execution (UID 1001)
- No privilege escalation
- Read-only root filesystem (where possible)
Secrets Management:
- K8s Secrets for DB credentials
- Azure Key Vault integration (recommended)
- No secrets in ConfigMaps or code
Network Security:
- SSL/TLS for DB connections
- Rate limiting at Ingress (50 req/s)
- Network Policies for tier isolation
12 / 16

## Slide 13
Resource Allocation
Compute and storage sizing for each tier
Component | CPU Request | CPU Limit | Memory Request | Memory Limit | Replicas
Apache2 (Web) | 100m | 500m | 128 Mi | 256 Mi | 2 - 10
Open Liberty (App) | 500m | 2000m (2 cores) | 512 Mi | 1 Gi | 2 - 8
Infrastructure | Specification | Details
AKS Node Pool | 3 x Standard_DS2_v2 | 2 vCPU, 7 GiB RAM per node
Container Registry | ACR Standard | Image storage and scanning
PostgreSQL | Standard_D2ds_v4 | 2 vCPU, 8 GiB RAM, 128 GB storage
Kubernetes | v1.29 | Azure CNI networking
Networking | Azure CNI | Pod-level IP addressing
Note: Resource requests guarantee minimum allocation; limits cap maximum usage. HPA will scale pods within min/max range based on actual utilization, optimizing cost.
13 / 16

## Slide 14
Key Benefits
Business and technical advantages of AKS migration
Automated Scaling
Scale from 2 to 10+ pods in seconds based on demand, eliminating manual VM provisioning that takes minutes to hours.
Zero-Downtime Deployments
Rolling updates ensure continuous availability during releases. Automated rollback if new versions fail health checks.
Self-Healing Infrastructure
Kubernetes automatically restarts failed containers, replaces unhealthy pods, and rebalances workloads across nodes.
Reduced Operational Overhead
Managed PostgreSQL eliminates DB admin tasks. AKS handles node patching, scaling, and monitoring.
Improved Security Posture
Network policies enforce tier isolation. Non-root containers, Azure Key Vault integration, and SSL everywhere.
Cost Optimization
Pay for actual resource consumption. Efficient bin-packing of pods on nodes. Scale down during low-traffic periods.
14 / 16

## Slide 15
Risk Mitigation & Rollback
Safety measures and recovery procedures
Rolling Update Strategy
maxSurge: 1 (add 1 pod before removing old)
maxUnavailable: 0 (never go below desired)
Liveness probes detect stuck pods
Readiness probes manage traffic routing
Startup probes allow slow initialization
30-60s graceful shutdown period
Rollback Procedures
kubectl rollout undo for instant rollback
Rollout history tracks all revisions
Rollback to specific version supported
Database rollback via point-in-time restore
ACR retains previous image versions
No data loss during application rollback
Health Monitoring
Liveness: Restart if /health fails 3x
Readiness: Remove from service if not ready
Startup: Wait for slow starts (up to 5 min)
AKS Monitoring: Azure Monitor add-on enabled
Ingress: Rate limiting at 50 req/s
Alerts: Set up for pod restarts and failures
15 / 16

## Slide 16
Timeline & Next Steps
Proposed execution plan
Phase | Duration | Key Activities | Deliverable
Phase 1: Infrastructure | 1 - 2 days | Provision Azure resources (RG, ACR, AKS, PostgreSQL) | Running AKS cluster
Phase 2: Data Migration | 1 day | Export, transfer, and restore PostgreSQL data | Verified database
Phase 3: Containerize & Deploy | 2 - 3 days | Build images, push to ACR, deploy K8s manifests | Running application on AKS
Phase 4: Verify & Optimize | 1 - 2 days | Health checks, performance testing, monitoring | Production-ready system
DNS Cutover & Go-Live | 1 day | Switch DNS, decommission VMs, final validation | Migration complete
Next Steps:
Approve migration plan and allocate Azure resources
Prepare application WAR file and static assets
Set up Azure Key Vault for production secrets
Configure DNS and TLS certificates
Schedule migration window with stakeholders
Plan parallel run period before VM decommission
16 / 16